## Slide 1
Executive Priority Requests
2025 Performance Outlook: ED Objectives
Municipal Services Sector
Notes: Note: Please after inserting your picture, “Right Click” on the picture and “Send it to Back” to get the “Gradient” effect.

## Slide 2: Content
Initiatives and expected outcomes
01
Executive Initiative #5 Proposed Work‑plan
02
Executive Initiative #10 Proposed Work‑plan
Pet‑Friendly Neighborhood Planning – Develop an action plan for three neighborhoods to become pet‑friendly (aligned with Planning & Mobility); weight = 9 %,
deadline Q3 2025
Stray‑Animal Population Control – Reduce the stray cat & dog population, improving the city image through sterilization, impounding and enforcement against abandonment, in line with DMT targets;
weight = 5 %,
deadline Q4 2025

## Slide 3: Executive Initiative #5 Proposed Work‑plan
Phase | Key Activities | Deliverables & KPIs
1 – Site Selection | Define selection criteria (population density, green‑space deficit, traffic volumes). Short‑list three zones with Planning Sector. | Report: justification & baseline map. KPI: neighborhoods approved (3).
2 – Baseline Audit | Field survey of parks, pedestrian links, pet‑waste bins, vet clinics. Analyses traffic circulation and public‑transport nodes. | Gap analysis (GIS layer).
3 – Design Package | Layout off‑leash dog areas, water stations, waste‑bag dispensers. Draft amendments to right‑of‑way standards for shared paths & crossings. Estimate CAPEX/OPEX. | Pet‑Friendly Toolkit (design standards + cost model).
4 – Stakeholder Engagement | Workshops with residents, Transport Sector, private developers. Collect feedback; refine design. | Engagement log & revised toolkit. KPI: ≥ 70 % resident satisfaction in survey.
5 – Implementation Road‑map | Phased construction plan (Q4 2025 – 2026). Assign responsibilities (Municipal Services, AD Mobility, contractors). | Final Action Plan with Gantt chart & quarterly progress metrics (e.g., Number of amenities installed).

## Slide 4: Executive Initiative #10 Proposed Work‑plan
Pillar | Actions | Indicators
A. Establish Baseline | City‑wide visual counts + analysis of complaint data. Map hot‑spots. | Baseline density (animals/km²) estimated Q2 2025.
B. Sterilisation (TNR) | Expand trap‑neuter‑return teams; partner with private vet clinics. Monthly sterilization quotas per hot‑spot. | % reduction in juvenile captures; ≥ 8 000 surgeries by Q4 2025.
C. Impounding & Adoption | Upgrade municipal shelter capacity. Launch digital adoption portal with vet‑checked animals. | Shelter occupancy ≤ 85 %; adoption rate ≥ 60 % of intakes.
D. Enforcement | Issue fines for abandonment & unlicensed breeding. Quarterly inspections of pet shops and markets. | # violations issued / collected; compliance > 90 %.
E. Public Awareness | Media campaign on responsible ownership; school outreach. Community volunteer programs for feeding stations under permit. | Campaign reach (impressions), volunteer hours logged.
F. Monitoring & Reporting | Quarterly KPI (dashboard if applicable) to DG & DMT. Adjust tactics based on trend analysis. | KPI reports delivered on time; ≥ 15 % population reduction by Q4 2025.

## Slide 5
Thank You
Municipal Services Sector
30/07/2025